## Worksheet
Task | Owner | Start Date | End Date | Status | Progress (%) | Dependencies | Notes
Define Productivity Goals | Sarah Johnson | 2024-04-01 | 2024-04-15 | In Progress | 65% | None | Align with departmental KPIs.
Conduct Stakeholder Workshops | Mark Davis | 2024-04-16 | 2024-04-28 | Planned | 0% | Goal Definition Complete | Target 15 participants.
Implement Time Tracking System | Lisa Chen | 2024-05-01 | 2024-05-31 | Not Started | 0% | Workshop Results Available | Select software with integration capabilities.
Analyze Productivity Data | James Reed | 2024-06-01 | 2024-06-15 | Planned | 0% | Time Tracking System Live | Compare with baseline performance.
Present Findings & Recommendations | Team Lead | 2024-07-01 | 2024-07-10 | Not Started | 0% | Data Analysis Complete | Include visual dashboards and key metrics.