## Project Tracker - Quarterly
Project Tracker – Productivity Improvement (Quarterly)
Project Name | Initiation Date | Target Completion Date | Status | Team Members | Key Activities (Q1) th> | Progress (%) th> | Risks & Challenges th> | Next Steps (Q2) th>
Streamline Workflow Automation | 2023-01-15 | 2023-04-30 | In Progress | Jane Smith, Mike Johnson, Sarah Lee | Process mapping, tool selection, pilot testing | 65% | Tool integration delays; employee resistance | Scale pilot to 3 departments; train users
Remote Team Collaboration Upgrade | 2023-02-01 | 2023-06-30 | Planning Phase | Alex Brown, Lisa Wong, David Kim | Needs assessment, vendor evaluation, ROI analysis | 20% | Lack of budget approval; competing priorities | Submit proposal to leadership by Q1 end
Reduce Meeting Overhead Initiative | 2023-03-10 | 2023-05-15 | On Track | Maria Garcia, Tom Reed, Chloe Patel | Meeting audit, scheduling optimization, templates rollout | 85% | Scheduling conflicts in cross-departmental teams | Implement AI-powered calendar sync by Q2
Enhance Employee Time Tracking System | 2023-04-052023-10-31 | Pending Approval | Nathan Foster, Priya Singh, Ryan White | System requirements gathering, UX design review | 15% | Compliance concerns; data privacy issues | Finalize compliance documentation by Q2 end