## Worksheet
Project ID | Project Name | Team Member | Start Date | End Date | Status | Progress (%) | Priority Level | Estimated Hours | Actual Hours
PRJ-001 | Enhance Workflow Automation Tools | Sarah Johnson | 2024-03-15 | 2024-06-30 | In Progress | 65% | High | 240 | 180
PRJ-002 | Implement Daily Stand-Up Meetings | Michael Chen | 2024-04-01 | 2024-05-31 | Completed | 100% | Medium | 80 | 75
PRJ-003 | Optimize Task Assignment System | Emma Rodriguez | 2024-03-28 | 2024-07-15 | Planning | 15% | High | 320 | 0
PRJ-004 | Introduce Time-Tracking Software | David Kim | 2024-05-10 | 2024-08-31 | Pending Approval | 0% | Critical | 400 | 0