## Worksheet
Project Name | Team Member | Start Date | End Date | Current Status | Priority Level | Progress (%) | Next Action | Responsible Owner
Enhance Team Collaboration Tools | Sarah Chen | 2024-03-15 | 2024-06-30 | In Progress | High | 65% | Conduct user testing in Q2 | David Kim
Optimize Daily Stand-Up Meetings | James Rivera | 2024-03-202024-05-31 | Planning | Medium | 30% | Finalize meeting template | Lisa Park
Automate Reporting Workflow | Amina Diallo | 2024-04-01 | 2024-07-15 | Not Started | High | 0% | Define automation scope and tools | Tom Wilson
Improve Task Assignment Process | Elena Martinez | 2024-03-18 | 2024-06-15 | In Progress | Medium | 55% | Train team on new system | Carlos Ruiz