## Worksheet
Task ID | Task Description | Assigned To | Priority | Due Date | Status | Estimated Time (hrs) | Progress (%) | Category | Deadline Compliance | Notes
TM-001 | Conduct market research for new product launch | Jane Doe | High | 2024-04-15 | In Progress | 15 | 65% | Marketing | On Track | Needs deeper customer feedback.
TM-002 | Develop project timeline and Gantt chart | John Smith | High | 2024-04-10 | Not Started | 8.5 | 0% | Project Management | Pending | Finalize with stakeholders.
TM-003 | Organize weekly team productivity review meetings | Lisa Brown | Moderate | 2024-04-25 | Completed | 3 | 100% | Operations | On Track | Team feedback collected.
TM-004 | Update internal workflow documentation | Mike Taylor | Low | 2024-05-05 | Not Started | 4 | 0% | Documentation | Pending | Include new tools.
TM-005 | Implement time-tracking software for team use | Sarah Wilson | High | 2024-04-30 | In Progress | 12 | 45% | Technology | On Track | User training scheduled for next week.