## Worksheet
Task ID | Task Description | Assigned To | Due Date | Priority Level | Estimated Hours | Actual Hours | Status | Budget Allocation ($) | Progress (%)
T001 | Conduct market analysis for Q4 products | Sarah Johnson | 2023-10-15 | High | 8 | 6.5 | In Progress | 1,200.00 | 81%
T002 | Develop new sales automation workflow | Michael Chen | 2023-11-05 | High | 12 | 0 | Not Started | 3,500.00 | 0%
T003 | Optimize email campaign performance | Emily Ross | 2023-10-30 | Medium | 4.5 | 4 | Completed | 800 | 100%
T004 | Update financial reporting dashboard | David Kim | 2023-11-10 | High | 6 | 5.2 | In Progress | 1,800.00 | 87%
T005 | Train team on new productivity tools | Lisa Wong | 2023-11-20 | Medium | 3 | 1.8 | In Progress | 600 | 60%