## Worksheet
Project Management – Financial View Balance Sheet
Category | Description | Allocated Budget (USD) | Actual Spend (USD) | Variance (USD) | Status
Project Initiation | Feasibility Study & Planning | 50,000 | 48,750 | +1,250 | On Track
R&D & Design | Prototype Development & Testing | 120,000 | 115,300 | +4,700 | On Track
Development & Build | Software Integration & Deployment | 300,000 | 298,500 | +1,500 | On Track
Testing & Quality Assurance | User Acceptance & Final Validation | 75,000 | 74,200 | 800 | On Track
Operations & Deployment | Pilot Launch & Support Setup | 60,000 | 58,900 | +1,100 | On Track
Total Budget (USD) |  | 605,000 | 597,650 | +7,350