## Worksheet
Activity | Budget Category | Estimated Cost (USD) | Allocation (%) | Responsible Team | Start Date | End Date | Status
Project Initiation | Planning & Feasibility | 15,000 | 10% | Project Office | 2024-03-15 | 2024-04-15 | Completed
Requirement Gathering | Business Analysis | 25,000 | 17% | Product Team | 2024-04-16 | 2024-05-31 | In Progress
Design Phase | UI/UX & Architecture | 40,000 | 27% | Design Team | 2024-06-01 | 2024-07-15 | Planned
Development Phase | Engineering & Coding | 120,000 | 75% | Engineering Team | 2024-07-16 | 2024-10-31 | Not Started
Testing & Quality Assurance | Quality Control | 20,000 | 13% | QA Team | 2024-11-01 | 2024-12-15 | Planned
Deployment & Go-Live | Operations & Launch | 15,000 | 10% | Operations Team | 2024-12-16 | 2024-12-31 | Not Started
Total Budget: |  |  | 100% | Estimated Total Cost: $235,000