## Worksheet
Task/Activity | Responsible Party | Start Date | End Date | Budget (USD) | Actual Cost (USD) | Status | Notes
Project Initiation | Project Manager | 2024-03-01 | 2024-03-15 | 5,000.00 | 4,850.00 | On Track | Feasibility studies and stakeholder alignment completed.
Requirements Gathering | Business Analyst | 2024-03-16 | 2024-04-10 | 8,500.00 | 8,230.00 | On Track | User interviews and documentation finalized.
Design Phase | UI/UX Designer | 2024-04-11 | 2024-05-15 | 12,000.00 | 11,750.00 | On Track | Wireframes and prototypes approved.
Development Phase | Software Development Team | 2024-05-16 | 2024-08-31 | 65,000.00 | 62,450.00 | On Track | Core features developed and tested.
Testing & Quality Assurance | QA Team | 2024-09-01 | 2024-09-30 | 15,000.00 | 14,950.00 | On Track | All critical bugs resolved.
Deployment & Go-Live | IT Operations | 2024-10-01 | 2024-10-15 | 7,500.00 | 7,480.00 | On Track | System deployed to production environment.
Post-Implementation Review | Project Manager | 2024-10-16 | 2024-10-31 | 3,000.00 | 2,950.00 | On Track | User feedback collected and lessons learned documented.