## Worksheet
Task/Activity | Responsible Employee | Estimated Cost (USD) | Actual Cost (USD) | Status | Progress (%)
Project Initiation & Planning | John Smith | 15,000 | 14,200 | Completed | 100%
Risk Assessment & Mitigation Planning | Sarah Johnson | 8,500 | 7,900 | Completed | 100%
Resource Allocation & Team Setup | Marcus Lee | 12,000 | 11,500 | In Progress | 75%
Scope Finalization & Approval | Lisa Wong | 6,000 | 5,800 | Pending Review | 60%
Development & Design Phase | Team A (All) | 50,000 | 32,500 | In Progress | 45%
Testing & Quality Assurance | Tomas Rivera | 18,000 | 14,700 | Scheduled | 20%
Project Closeout & Review | All Team Members | 5,000 | - | Pending | 0%
Total Estimated Cost |  |  | $96,500 | Total Actual Cost (as of now)
Budget Variance |  |  | $1,200 (Under Budget)