## Worksheet
Activity | Duration (days) | Responsible Party | Budget Allocation ($) | Actual Spend ($) | Variance ($) | Status
Project Initiation | 10 | Project Manager | 15,000 | 14,800 | 200 | On Track
Requirements Gathering | 25 | Business Analysts | 30,000 | 29,500 | 500 | On Track
Design Phase | 30 | Design Team | 45,000 | 44,200 | 800 | On Track
Development Phase | 60 | Engineering Team | 120,000 | 118,500 | +1,500 | On Track
Testing & QA | 20 | QA Team | 25,000 | 24,800 | 200 | On Track
Deployment & Go-Live | 7 | Operations Team | 10,000 | 10,200 | -200 | On Track
Post-Implementation Review | 5 | Project Manager & Stakeholders | 5,000 | 5,000 | 0 | On Track
Total Budget |  |  |  |  | 250,000 | 249,800