## Worksheet
Project Name | Phase | Budget Category | Estimated Cost (USD) | Allocation % | Responsible Team | Start Date | End Date
Website Redesign Project | Discovery & Planning | Feasibility Study | 15,000.00 | 10% | Strategy Team | 2024-03-15 | 2024-04-30
Website Redesign Project | Design & Development | UI/UX Design | 75,000.00 | 50% | Design Team | 2024-05-01 | 2024-07-15
Website Redesign Project | Testing & Launch | QA Testing | 20,000.00 | 13% | QA Team | 2024-08-15 | 2024-08-31
Mobile App Development | Concept & Prototyping | Product Mockups | 30,000.00 | 15% | Product Team | 2024-04-15 | 2024-06-30
Mobile App Development | Development & Integration | Backend Development | 120,000.00 | 65% | Engineering Team | 2024-07-15 | 2024-11-30
Total Budget (USD) |  |  | 240,000.00 | 100% | Office Use – Project Management Budget Template