## Worksheet
Project Name | Phase | Budget Category | Estimated Cost (USD) | Allocated Funds (USD) | Percent Complete | Notes
Website Redesign | Planning | Design & Research | 5,000 | 3,200 | 64% | User surveys completed; wireframes approved.
Mobile App Development | Development | Frontend & Backend | 20,000 | 8,500 | 42.5% | UI/UX design in progress; APIs under review.
Marketing Campaign | Execution | Advertising & Promotion | 15,000 | 4,200 | 28% | Social media ads launched; ROI tracking begins.
Training & Onboarding | Post-Implementation | Human Resources | 3,000 | 1,500 | 50% | Training materials finalized; sessions scheduled.