## Worksheet
Task | Responsible Party | Start Date | End Date | Budget Allocation (USD) | Status | Progress (%)
Project Initiation | Project Manager | 2024-01-01 | 2024-01-15 | 5,000 | Completed | 100%
Requirements Gathering | Business Analysts | 2024-01-16 | 2024-02-15 | 8,000 | In Progress | 75%
Design Phase | UX/UI Design Team | 2024-02-16 | 2024-03-31 | 15,000 | Not Started | 0%
Development Phase | Engineering Team | 2024-04-01 | 2024-06-30 | 50,000 | Not Started | 0%
Testing & QA | QA Team | 2024-07-01 | 2024-08-15 | 12,000 | Not Started | 0%
Deployment & Go-Live | IT Operations | 2024-08-16 | 2024-08-31 | 5,500 | Not Started | 0%
Post-Launch Review | Project Manager | 2024-09-01 | 2024-09-30 | 3,500 | Not Started | 0%
Total Budget: |  |  | $99,000