## Worksheet
Activity | Estimated Cost (USD) | Responsible Person | Start Date | End Date | Status
Project Planning | $5,000 | Jane Smith | 2024-01-15 | 2024-01-31 | Completed
Requirement Analysis | $8,000 | John Doe | 2024-02-01 | 2024-02-15 | In Progress
Design Phase | $15,000 | Lisa Brown | 2024-03-01 | 2024-03-31 | Pending Approval
Development Phase | $50,000 | Team A | 2024-04-01 | 2024-06-30 | Not Started
Testing & Quality Assurance | $12,000 | Mike Wilson | 2024-07-01 | 2024-08-15 | Planned
Deployment & Training | $7,500 | Sarah Lee | 2024-09-01 | 2024-09-30 | Not Started