## Worksheet
Activity | Budget Allocation |  |  | Responsible Team Member | Start Date | End Date | Status
| Estimated Cost ($) | Allocated Cost ($) | Variance ($)
Project Initiation | 10,000 | 10,000 | 0 | Sarah Johnson | 2024-03-15 | 2024-03-31 | Completed
Requirements Gathering | 25,000 | 24,500 | -500 | Mike Chen | 2024-04-01 | 2024-04-15 | In Progress
Design Phase | 35,000 | 32,000 | -3,000 | Lena Patel | 2024-04-16 | 2024-05-15 | Pending Approval
Development & Testing | 80,000 | 76,200 | -3,800 | David Kim | 2024-05-16 | 2024-07-15 | In Progress
Deployment & Training | 20,000 | 18,500 | -1,500 | Nina Torres | 2024-07-16 | 2024-07-31 | Planned
Post-Launch Review | 5,000 | 5,000 | 0 | Raj Singh | 2024-08-01 | 2024-08-15 | Pending
Total Budget |  |  | $155,000 | Total Allocated |  |  | $156,200