## Worksheet
Section | Description | Responsibility | Timeline | Status
1. Project Overview | Clear definition of project goals, scope, and deliverables. | Project Manager | Week 1 | Completed
2. Objectives & Goals | Specific, measurable, achievable, relevant, and time-bound (SMART) goals. | Project Sponsor & Manager | Week 2 | In Progress
3. Stakeholder Analysis | Identification and assessment of key stakeholders and their expectations. | Stakeholder Coordinator | Week 3 | Pending
4. Risk Management Plan | Identification, assessment, and mitigation strategies for potential risks. | Risk Officer | Week 4 | Not Started
5. Budget & Costing | Detailed cost estimation, funding sources, and financial controls. | Finance Manager | Week 5 | Not Started
6. Work Breakdown Structure (WBS) | Division of project into manageable tasks and subtasks. | Project Manager & Team Lead | Week 6 | Pending
7. Schedule & Milestones | Timeline of key activities and deadlines with dependencies. | Scheduling Specialist | Week 7 | Not Started
8. Communication Plan | Defined methods, frequency, and channels for stakeholder communication. | Communications Officer | Week 8 | Pending
9. Success Metrics & KPIs | Measurable indicators to evaluate project performance and success. | Performance Analyst | Week 9 | Not Started
10. Closure & Review | Process to close the project, document lessons learned, and conduct evaluation. | Project Manager | Post-Completion | Not Started