## Worksheet
Section | Key Elements | Responsibility | Timeline | Status
1. Project Overview | Project goals, scope, objectives, deliverables | Project Lead & PMO | Week 1–2 | Pending Review
2. Stakeholder Analysis | Identify key stakeholders, interests, communication needs | Stakeholder Manager | Week 2–3 | In Progress
3. Work Breakdown Structure (WBS) | Detailed tasks, sub-tasks, milestones | Team Leads & PMO | Week 3–4 | Not Started
4. Risk Management Plan | Risks identified, mitigation strategies, owners | Risk Officer & Team | Week 4–5 | Planning Phase
5. Resource Allocation | Team assignments, tools, budget breakdown | HR & Project Manager | Week 5–6Pending Approval
6. Communication Plan | Frequent updates, meetings, reporting cadence | Communication Lead | Week 3–4 | Approved
7. Budget & Financials | Cost estimates, funding sources, forecast | Finance Team | Week 5–6 | Draft Finalized
8. Performance & Milestones | KPIs, success metrics, review points | Project Manager & Team | Ongoing (Monthly) | Baseline Set
9. Change Management | Process for handling scope, timeline, budget changes | Project Manager & PMO | Week 4–6 | In Development
10. Closure & Evaluation | Final review, lessons learned, post-project report | Project Lead & Stakeholders | Post-Completion (Month 6) | Pending