## Worksheet
Project Name | Phase | Start Date | End Date | Responsible Team | Status | Progress (%) | Budget (USD) | Key Milestones | Risks & Dependencies
Digital Transformation Initiative | Planning | 2024-03-15 | 2024-06-30 | IT & Strategy Team | On Track | 75% | $250,000 | Feasibility study complete, Stakeholder alignment secured | Data migration risk; Vendor onboarding delay
Customer Experience Enhancement | Execution | 2024-04-01 | 2024-10-31 | Customer Success & UX Team | Active | 55% | $180,000 | UI redesign launch (Q3), Support training rollout | Resource shortage; Change resistance from legacy teams
Supply Chain Optimization | Monitoring | 2024-05-10 | 2024-12-31 | Operations & Logistics Team | On Hold | 30% | $320,000 | Vendor audit complete, New routing model in review | Regulatory changes; Delay in supplier response