## Worksheet
Project Name | Status | Start Date | End Date | Budget (USD) | Current Spend | Progress % | Owner | Next Milestone | Risk Level
Digital Transformation Initiative | On Track | Jan 15, 2024 | Sep 30, 2024 | $500,000 | $315,400 | 73% | Sarah Thompson | Q3 Launch of New Platform | Medium
Customer Experience Upgrade | At Risk | Mar 05, 2024 | Nov 15, 2024 | $375,000 | $289,600 | 77% | James Reed | Final UX Audit (Dec) | High
Cloud Migration Project | On Track | Feb 10, 2024 | Aug 31, 2024 | $650,000 | $498,500 | 76% | Lisa Chen | Data Backup Validation | Medium
Product Roadmap Expansion | In Planning | Apr 01, 2024 | Dec 31, 2024 | $800,000 | $0 | – | Michael Torres | Phase I Requirements Finalized | Low