## Worksheet
Project Phase | Key Objectives | Milestones | Timeline (Weeks) | Team Roles | Budget Allocation
Discovery & Feasibility | Define business needs, validate market demand, assess technical viability | Stakeholder interviews completed Feasibility report approved | Weeks 1–4 | Project Lead, Product Manager, UX Researcher | $15,000
Product Design & Prototyping | Create wireframes, user flows, and interactive prototypes | Design system finalized Prototype reviewed & approved | Weeks 5–8 | UX Designer, UI Designer, Product Manager | $25,000
Development & Build | Develop core features, integrate APIs, conduct QA testing | MVP launched Alpha version released | Weeks 9–20 | Full Development Team, QA Engineer, DevOps Lead | $80,000
Testing & Launch | Conduct user testing, fix critical bugs, prepare go-to-market plan | Beta launch completed Official launch date set | Weeks 21–24 | Product Manager, QA Lead, Marketing Coordinator | $10,000
Post-Launch & Iteration | Collect user feedback, plan feature updates, monitor performance | First user feedback report Quarterly roadmap approved | Weeks 25–52 | Product Manager, Data Analyst, Customer Support | $20,000 (ongoing)