## Worksheet
Task | Assigned To | Start Date | End Date | Status | Progress (%) | Priority | Dependencies | Notes
Project Initiation | John Doe | 2024-03-01 | 2024-03-15 | Completed | 100% | Low |  | Finalized project scope and objectives.
Requirement Gathering | Jane Smith | 2024-03-16 | 2024-04-10 | In Progress | 65% | Medium | Project Initiation | Interviews with stakeholders ongoing.
Design Phase | Mike Johnson | 2024-04-11 | 2024-05-05 | Planned | 0% | High | Requirement Gathering | Wireframes and UX mockups to be created.
Development | Team A | 2024-05-06 | 2024-07-31 | Not Started | 0% | High | Design Phase | Frontend and backend coding will begin.
Testing & QA | Sarah Lee | 2024-08-01 | 2024-08-31 | Not Started | 0% | Medium | Development | Functional and performance testing planned.
Deployment | IT Team | 2024-09-01 | 2024-09-05 | Not Started | 0% | Low | Testing & QA | Live environment rollout scheduled.