## Worksheet
Project Name | Team Member | Task Assigned | Due Date | Status | Progress (%) | Remarks
Website Redesign | Sarah Johnson | UI/UX Design Finalization | 2023-10-15 | Completed | 100% | Approved by stakeholders.
Mobile App Development | David Kim | <Backend API Setup | 2023-10-20 | In Progress | 65% | Testing phase delayed by third-party service.
Marketing Campaign | Lena Rodriguez | Social Media Content Creation | 2023-10-18 | Pending | 30% | Waiting on brand guidelines approval.
Client Onboarding | James Wilson | Documentation & Setup | 2023-10-25 | Delayed | 40% | Client feedback required for final requirements.