## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%) | Notes
Project Kickoff Meeting | Sarah Johnson | 2024-04-01 | Completed | High | 100% | All stakeholders aligned on goals and scope.
Requirement Gathering | David Chen | 2024-04-15 | In Progress | High | 60% | Finalize stakeholder input by end of week.
Design Finalization | Lena Patel | 2024-05-01 | Not Started | Medium | 0% | Review wireframes with product team.
Development Phase Start | Michael Torres | 2024-05-10 | Not Started | High | 0% | Codebase setup and API integration.
Testing & QA Review | Emma Wright | 2024-06-05 | Planned | High | 0% | Include user acceptance testing.
Project Launch & Deployment | Team Lead (All) | 2024-06-15 | Not Started | Critical | 0% | Full rollout with post-launch monitoring.