## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%)
Project Kickoff Meeting | Alex Johnson | 2024-04-01 | Completed | High | 100%
Requirement Gathering | Samira Khan | 2024-04-15 | In Progress | High | 65%
Design Finalization | Jordan Lee | 2024-05-01 | Planned | Medium | 0%
Development Phase Start | Morgan Reed | 2024-05-10 | Not Started | High | 0%
Quality Assurance Testing | <Taylor Wu | 2024-06-01 | Blocked | High | 0%
User Training Sessions | Casey Park | 2024-06-15 | Completed | Medium | 100%