## Worksheet
Task | Assigned To | Due Date | Priority | Status | Start Date | Estimated Hours | Actual Hours | Progress (%) | Dependencies | Notes/Comments
Project Kickoff Meeting | Project Manager | 2024-04-01 | High | Completed | 2024-03-25 | 4 | 4.5 | 100% | None
Requirements Gathering | Business Analyst | 2024-04-15 | High | In Progress | 2024-03-30 | 8 | 5.5 | 68% | Approval from Stakeholders | Finalize scope with client via call
Design Phase - UI/UX | UI/UX Designer | 2024-05-10 | Medium | Not Started |  | 12 | 0 | 0% | Requirements Approved | Create wireframes and mockups for key screens
Development Phase - Backend | Senior Developer | 2024-06-05 | High | Not Started |  | 24 | 0 | 0% | Design Finalized | Set up database schema and APIs
Testing & QA | QA Engineer | 2024-07-10 | High | Not Started |  | 16 | 0 | 0% | Backend Ready | Run unit, integration, and user acceptance tests
Deployment & Go-Live | DevOps Engineer | 2024-07-25 | High | Not Started |  | 8 | 0 | 0% | QA Sign-off | Deploy to production environment with backup plan
Post-Launch Review | Project Manager | 2024-08-05 | Medium | Not Started |  | 4 | 0 | 0% | Go-Live Complete | Collect feedback and document lessons learned