## Worksheet
Task | Owner | Due Date | Status | Priority | Notes
Project Kickoff Meeting | John Doe | 2024-04-01 | Completed | High | All stakeholders attended; project scope finalized.
Requirements Gathering | Jane Smith | 2024-04-15 | In Progress | High | Interviews with key users scheduled.
Design Phase Initiation | Mike Johnson | 2024-05-01 | Not Started | Medium | Wireframes to be developed by end of April.
Development Start | Sarah Lee | 2024-05-15 | Not Started | High | Backend and frontend development to begin.
Testing & QA Cycle | David Brown | 2024-06-10 | Not Started | High | Include user acceptance testing and bug resolution.
Project Review & Final Approval | Lisa Chen | 2024-07-01 | Not Started | High | Final sign-off before deployment.