## Worksheet
Task | Owner | Due Date | Status | Notes
Project Kickoff Meeting | Sarah Johnson | 2024-04-01 | Completed | All stakeholders aligned on goals and timelines.
Scope Definition Document | Mike Chen | 2024-04-10 | In Progress | Final version due by end of week.
Resource Allocation Plan | Lena Rodriguez | 2024-04-15 | Pending | Waiting on team availability confirmation.
Risk Assessment & Mitigation | David Kim | 2024-04-20 | Not Started | Initial draft to be reviewed by PMO.
Weekly Progress Report | Team Lead | 2024-04-25 | Completed | Shared with client via email.
Client Review Meeting | Sophia Williams | 2024-05-01 | Scheduled | Agenda to be sent by April 30.