## Worksheet
Project Management - Monthly Chore Chart
Date | Task | Owner | Due Date | Status | Priority | Notes
Monday, Apr 8 | Project Kickoff Meeting | John Smith | Apr 8, 2024 | Completed | HIGH | Finalize project scope and objectives.
Tuesday, Apr 9 | Team Onboarding | Sarah Lee | Apr 10, 2024 | In Progress | MEDIUM | Distribute project documentation.
Wednesday, Apr 10 | Requirement Gathering Workshop | Mike Chen | Apr 12, 2024 | Pending | HIGH | Collect input from stakeholders.
Thursday, Apr 11 | Weekly Progress Review | All Team | Apr 11, 2024 | Completed | MEDIUM | Discuss roadblocks and updates.
Friday, Apr 12 | Finalize Project Timeline | Lisa Wong | Apr 15, 2024 | Scheduled | HIGH | Update Gantt chart with milestones.
Saturday, Apr 13 | Client Presentation Draft | John Smith | Apr 16, 2024 | Not Started | HIGH | Prepare slides and key messages.
Sunday, Apr 14 | Team Retrospective Meeting | Sarah Lee | Apr 15, 2024 | In Progress | MEDIUM | Review process improvements.
Monthly Chore Chart – Project Management • Updated April 2024