## Worksheet
Project Management | Chore Chart - Quarterly
Q1 – January to March
Week | Responsibility | Due Date
Week 1 | Project Kickoff Meeting & Goals Setting | Jan 5
Week 2 | Team Role Assignment & RACI Matrix Finalization | Jan 12
Week 3 | Scope Definition & Stakeholder Review | Jan 19
Week 4 | Work Breakdown Structure (WBS) Drafting | Jan 26
Q2 – April to June | Responsibility | Due Date
Week 1 | WBS Final Approval & Task Estimation | Apr 3
Week 2 | Schedule Development & Milestone Planning | Apr 10
Week 3 | Resource Allocation & Budget Drafting | Apr 17
Week 4 | Project Risk Assessment & Mitigation Plan | Apr 24
Q3 – July to September | Responsibility | Due Date
Week 1 | Project Baseline Approval (Schedule & Budget) | Jul 4
Week 2 | Team Training & Tool Setup | Jul 11
Week 3 | Progress Tracking Initiation (Weekly Reports) | Jul 18
Week 4 | Quarterly Review Meeting Preparation | Jul 25
Q4 – October to December | Responsibility | Due Date
Week 1 | Final Review & Project Closure Planning | Oct 2
Week 2 | Deliverable Finalization & Documentation | Oct 9
Week 3 | Performance Review & Lessons Learned Report | Oct 16
Week 4 | Project Closure & Stakeholder Sign-Off | Oct 23