## Worksheet
Task | Owner | Due Date | Status | Priority
Project Kickoff Meeting | Jane Doe | 2024-04-01 | Completed | High
Requirements Gathering | John Smith | 2024-04-15 | In Progress | High
Design Finalization | Lisa Chen | 2024-05-10 | Pending | Medium
Development Start | Mike Brown | 2024-05-20 | Not Started | High
Testing Phase | Sarah Lee | 2024-06-15 | Not Started | Medium
Client Review & Approval | Team Lead | 2024-07-01 | Pending | High
Go-Live & Handover | All Team Members | 2024-07-15 | Not Started | High