## Worksheet
Task | Assignee | Due Date | Status | Notes
Project Kickoff Meeting | Team Lead | 2024-04-01 | Completed | All stakeholders attended.
Define Project Scope | Product Manager | 2024-04-08 | In Progress | Draft scope document under review.
Create Work Breakdown Structure | Project Coordinator | 2024-04-15 | Not Started
Schedule Team Meetings | Team Lead | 2024-04-10 | Completed | Weekly syncs set for every Monday.
Risk Assessment Workshop | Risk Officer | 2024-04-22 | Not Started