## Worksheet
Task | Assignee | Due Date | Status | Priority | Progress (%)
Project Kickoff Meeting | Alice Johnson | 2023-10-05 | Completed | Medium | 100%
Scope Definition Document | Bob Smith | 2023-10-12 | In Progress | High | 65%
Risk Assessment & Mitigation Plan | Carol Davis | 2023-10-19 | Pending | High | 0%
Resource Allocation Review | David Lee | 2023-10-26 | Completed | Medium | 100%
Stakeholder Approval Process | Elena Martinez | 2023-11-03 | In Progress | High | 40%