## Worksheet
Client Name | Project Title | Start Date | End Date | Project Manager | Budget (USD) | Status | Priority Level | Scope Description | Milestones | Key Deliverables | Risk Assessment | Communication Plan | Dependencies | Progress Report Date
Global Tech Solutions Inc. | Cloud Migration Initiative | 2024-03-15 | 2024-09-30 | Sarah Johnson | $150,000 | On Track | High | Migrate all on-premise servers to AWS with zero downtime. | Phase 1: Setup (Mar 15–Apr 30) Phase 2: Migration (May 1–Jul 15) Phase 3: Testing (Aug 1–Aug 30) | Cloud architecture documentation, security audit report, performance dashboard | Data loss risk – mitigated via backup strategy. | Weekly meetings with stakeholders; bi-weekly progress updates. | Vendor onboarding timeline, network availability | 2024-07-10
BrightFuture Education Ltd. | LMS Platform Development | 2024-04-01 | 2025-01-31 | Michael Chen | $250,000 | Active (Planning) | Medium | Design and develop a scalable Learning Management System with mobile compatibility. | User research (Apr 1–May 15) UI/UX design (May 16–Jun 30) Development (Jul 1–Dec 31) | User interface, course management module, analytics dashboard | Integration with third-party tools – delayed due to API changes. | Monthly sprint reviews; weekly stand-ups with developers. | Third-party API access, server infrastructure | 2024-06-15
Nexus Healthcare Group | Patient Portal Launch | 2024-05-01 | 2024-11-30 | Lisa Park | $95,000 | In Progress | High | Launch a secure web portal for patient appointments and records access. | Beta testing (May 15–Jul 31) Regulatory compliance review (Aug 1–Sep 30) Go-live (Oct 1–Nov 30) | Secure login system, appointment scheduling, medical history access | HIPAA compliance risk – audit pending. | Daily updates to stakeholders; monthly security reports. | HIPAA certification process, existing CRM integration | 2024-08-25