## Worksheet
Project ID | Project Name | Owner | Start Date | End Date | Status | Budget (USD) | Actual Spend (USD) | Progress (%) | Next Milestone | Risk Level | CRS Update Date
PM-2023-001 | Customer Onboarding Platform | Sarah Johnson | 2023-04-01 | 2023-09-30 | On Track | 500,000 | 415,250 | 83% | Q3 Delivery Review | Low | 2023-06-15
PM-2023-002 | Cloud Migration Initiative | Michael Chen | 2023-05-10 | 2024-01-31 | In Progress | 850,000 | 623,400 | 73% | Phase 2 Integration | Medium | 2023-07-10
PM-2023-003 | AI Customer Support Pilot | Emily Rodriguez | 2023-11-05 | 2024-03-31 | Planned | 375,000 | - | 0% | Pilot Launch (Q1) | Low | 2023-12-01
PM-2023-004 | Marketing Automation Upgrade | David Kim | 2023-07-15 | 2023-12-15 | Completed | 200,000 | 198,750 | 99% | Final Audit & Handover | None | 2023-12-10