## Worksheet
Task | Assigned To | Due Date | Status | Priority | Progress (%)
Project Kickoff Meeting | John Doe | 2023-10-05 | Completed | Low | 100%
Requirement Gathering | Jane Smith | 2023-10-15 | In Progress | Medium | 60%
Design Phase Finalization | Mike Johnson | 2023-11-01 | Pending | High | 0%
Development Start | Sarah Lee | 2023-11-10In Progress | Medium | 40%
Testing & Quality Assurance | David Brown | 2023-12-05 | Pending | High | 0%