## Worksheet
Project Name | Client Name | Start Date | End Date | Status | Assigned To | Budget (USD) | Actual Spend (USD) | Next Milestone | Priority Level
Website Redesign | TechNova Inc. | 2024-03-15 | 2024-06-30 | On Track | Sarah Johnson | 150,000 | 125,400 | Launch Phase 2 | High
CRM Integration Project | Global Solutions Ltd. | 2024-04-01 | 2024-08-15 | In Progress | Michael Lee | 80,000 | 45,200 | Data Migration Complete | Medium
Mobile App Development | InnovateX Co. | 2024-05-10 | 2025-01-31 | Planning | Emily Chen | 200,000 | - | UI/UX Design Review | High
Client Onboarding System | QuickStart Agency | 2024-06-05 | 2024-11-30 | Delayed | David Patel | 75,000 | 62,100 | Training Phase Delayed | Medium