## Worksheet
Project ID | Project Name | Client Name | Start Date | End Date | Project Manager | Budget (USD) | Current Status | Priority Level | Milestones | Risk Assessment | Communication Plan | Progress Report (Last Update) | Next Review Date | Assigned Resources
PM-2023-001 | E-commerce Platform Upgrade | Global Retail Inc. | 2023-10-01 | 2024-03-31 | Sarah Johnson | $500,000 | On Track | High | Launch v2.1, QA Completion, Go-Live | Medium (Data Migration Risk) | Weekly calls; bi-weekly status reports | Completed Q4 Sprint 3 | 2024-01-15 | Dev Team, UX Designer, QA Lead
PM-2023-002 | Customer Support Automation | TechSolutions LLC | 2023-11-15 | 2024-06-30 | Michael Chen | $350,000 | Active (Delay Risk) | Medium | Phase 1 Testing, AI Integration | High (Integration with Legacy Systems) | Daily syncs; weekly demos | Testing Phase Ongoing | 2024-02-01 | IT Team, AI Specialist, Support Lead
PM-2023-003 | Marketing Campaign Expansion | Bright Future Media | 2023-12-01 | 2024-05-31 | Lisa Park | $475,000 | Planning Phase | Low | Audience Research, Creative Approval | Low (Budget Overrun Risk) | Bi-weekly meetings with creative team | Initial strategy drafted | 2024-01-30 | Marketing Manager, Copywriter, Analyst