## Worksheet
Project Name | Client Name | Start Date | End Date | Status | Primary Contact | Budget (USD) | Progress (%) | Next Milestone | Assigned Team | CRM Source | Notes
E-Commerce Platform Launch | TechNova Inc. | 2024-03-01 | 2024-07-31 | On Track | Sarah Chen | $500,000 | 75% | Q2 UI Finalization | Frontend & Dev Ops | LinkedIn Lead | Client requested agile sprints for faster delivery.
Customer Support Automation | SupportGlobal Ltd. | 2024-04-15 | 2024-11-30 | Planning | David Miller | $320,000 | 25% | Phase 1: RFP Review | Product & AI Team | CRM Portal Assignment | Integration with existing helpdesk system is pending approval.
Mobile App Redesign | AppFlow Solutions | 2024-05-10 | 2024-10-15 | In Progress | Lena Patel | $450,000 | 50% | User Testing Phase | UX & Mobile Dev | Cold Call Lead | Feedback collected from beta users will be reviewed next week.
Cloud Migration Initiative | DataEdge Corp. | 2024-06-01 | 2024-12-31 | Pending Approval | James Reed | $800,000 | 15% | Security Audit Completion | Infrastructure & Security Team | Internal Proposal Submission | Awaiting final sign-off from CTO.