## Worksheet
Project Name | Client Name | Start Date | End Date | Status | Priority | Owner | Next Milestone | Budget (USD) | Progress (%)
Website Redesign | TechNova Inc. | 2024-03-15 | 2024-06-30 | On Track | High | Sarah Johnson | UI/UX Final Review (May 10) | $50,000 | 75%
CRM System Implementation | Global Sales Ltd. | 2024-04-01 | 2024-08-31 | In Progress | Medium | David Chen | Data Migration (June 15) | $120,000 | 45%
Mobile App Development | MobileFirst Corp. | 2024-05-10 | 2024-11-30 | Planned | High | Lisa Rodriguez | Prototype Approval (July 20) | $180,000 | 10%
Market Expansion (Europe) | Worldwide Brands | 2024-06-01 | 2025-03-31 | Pending Approval | Low | Mark Thompson | Budget Finalization (July 5) | $250,000 | 0%