## Worksheet
Date | Task | Assigned To | Priority | Status | Estimated Time (hrs) | Actual Time (hrs) | Notes
2024-04-05 | Review project scope document | John Smith | High | In Progress | 2 | 1.5 | Need to align with stakeholders on deliverables.
2024-04-05 | Prepare daily stand-up meeting agenda | Sarah Lee | Medium | Completed | 0.5 | 0.5 | Shared with team via email.
2024-04-06 | Update project timeline with new milestones | Mike Johnson | High | Not Started | 3 | - | Waiting for approval from PMO.
2024-04-06 | Conduct risk assessment session | Emma Watson | Medium | In Progress | 4 | 2 | Identified three major risks; documented in risk register.
2024-04-07 | Submit weekly progress report | All Team Members | Medium | Completed | 1 | 1 | Submitted to project manager and stakeholders.