## Worksheet
Date | Project Name | Task Description | Assigned To | Start Time | End Time | Status | Priority | Notes
2023-10-05 | Website Redesign | Finalize UI/UX wireframes | Sarah Johnson | 09:00 | 12:00 | In Progress | High | Need client feedback by end of day.
2023-10-05 | Mobile App Development | Develop login module | Mike Chen | 13:00 | 16:00 | Not Started | Medium | Integration with backend API required.
2023-10-05 | Marketing Campaign | Draft social media calendar | Lisa Rodriguez | 08:00 | 10:30 | Completed | Low | Approved by marketing lead.
2023-10-06 | Website Redesign | Review client feedback on wireframes | Sarah Johnson | 10:00 | 13:00 | Not Started | High | Schedule meeting with client on Friday.