## Worksheet
Task | Priority | Estimated Time | Assigned To | Status | Due Date
Product Requirements Gathering | High | 3 hours | Alex Morgan | In Progress | 2024-04-05
UI/UX Wireframe Design | High | 4 hours | Samira Patel | Completed | 2024-04-03
Frontend Development (Phase 1) | Medium | 8 hours | Jordan Lee | Pending | 2024-04-07
Backend API Integration | High | 10 hours | Taylor Kim | Not Started | 2024-04-10
Daily Stand-up Meeting (9 AM) | Low | 30 minutes | Team Lead | Completed | 2024-04-05