## Worksheet
Week | Project Phase | Budget Allocation ($) | Actual Spend ($) | Variance ($) | Status | Responsible Team
Week 1 | Initiation & Feasibility | 15,000 | 12,500 | +2,500 | On Track | Project Office
Week 2 | Scope Definition | 20,000 | 19,800 | <+200 | On Track | Business Analysts
Week 3 | Resource Planning | 18,000 | 17,200 | 800 | On Track | HR & Operations
Week 4 | Requirements Gathering | 30,000 | 28,500 | +1,500 | On Track | User Experience Team
Week 5 | Design Development | 40,000 | 38,700 | +1,300 | On Track | UI/UX Designers
Total Budget: |  |  | $133,500 | $127,700 | — | —