## Worksheet
Task | Responsible Party | Start Date | End Date | Budget (USD) | Current Status | Pending Expenses
Project Initiation | Project Manager | 2024-01-01 | 2024-01-15 | 5,000.00 | On Track | $0.00
Requirements Gathering | Business Analyst | 2024-01-16 | 2024-02-15 | 8,500.00 | On Track | $1,200.00
Design Phase | UX/UI Designer | 2024-02-16 | 2024-03-31 | 15,000.00 | In Progress | $3,800.00
Development Phase | Software Developers | 2024-04-01 | 2024-06-30 | 65,000.00 | Planning Phase | $12,500.00
Testing & QA | QA Engineer | 2024-07-01 | 2024-08-15 | 12,000.00 | Not Started | $0.00
Deployment & Go-Live | DevOps Team | 2024-08-16 | 2024-08-31 | 5,000.00 | Not Started | $0.00