## Worksheet
Task | Responsible Party | Start Date | End Date | Budget Allocation (USD) | Status | Progress (%) | Milestones | Risks & Issues | Dependencies
Project Initiation | Project Manager | 2024-03-01 | 2024-03-15 | 5,000.00 | Completed | 100% | Feasibility study approved | None | -
Requirements Gathering | Business Analysts | 2024-03-16 | 2024-04-10 | 8,500.00 | In Progress | 65% | Final requirement sign-off by stakeholders | Stakeholder feedback delays | Project Initiation
Design Phase | UX & Development Team | 2024-04-11 | 2024-05-30 | 15,000.00 | Planned | 0% | Wireframes approved, prototype ready | Design tool licensing delay | Requirements Gathering
Development & Testing | Developers, QA Team | 2024-06-01 | 2024-08-15 | 30,000.00 | Not Started | 0% | Alpha testing complete, beta launch ready | Third-party API downtime risk | Design Phase
Deployment & Training | Operations Team, Support Staff | 2024-08-16 | 2024-09-30 | 7,500.00 | Planned | 0% | System goes live, user training completed | User adoption below expectations | Development & Testing
Post-Implementation Review | Project Manager, Stakeholders | 2024-10-01 | 2024-10-31 | 3,000.00 | Not Started | 0% | Final performance report and lessons learned | Resource reallocation needed | Deployment & Training
Total Budget Allocation |  |  |  |  | 69,000.00