## Worksheet
Project Phase | Budget Allocation (USD) | Responsible Team | Timeline (Months) | Key Deliverables | Status
Initiation | $50,000 | Project Office | 1-2 | Feasibility Study, Stakeholder Analysis | On Track
Planning | $120,000 | Project Management Team | 3-4 | Work Breakdown Structure, Risk Register, Schedule Plan | In Progress
Execution | $400,000 | Operations & Development Teams | 5-9 | Product Development, Resource Deployment, Team Training | Pending Start
Monitoring & Control | $80,000 | Project Oversight Committee | Ongoing | Performance Reports, Variance Analysis, Adjustments | Active
Closure | $30,000 | Project Office & Finance | 10-12 | Final Report, Budget Audit, Lessons Learned | Not Started