## Worksheet
Project Phase | Budget Allocation (USD) | Start Date | End Date | Responsible Team | Status
Initiation | 15,000 | 2024-03-01 | 2024-03-31 | Project Steering Committee | Completed
Planning | 40,000 | 2024-04-01 | 2024-05-31 | Project Manager & Team Lead | In Progress
Execution | 120,000 | 2024-06-01 | 2024-11-30 | Operations & Development Teams | Not Started
Monitoring & Control | 30,000 | 2024-07-01 | Ongoing | Project Oversight Team | Planned
Closure | 10,000 | 2025-01-01 | 2025-01-31 | Project Closure Team | Not Started