## Worksheet
Date | Project Phase | Task Description | Assigned To | Estimated Hours | Actual Hours | Status | Budget Allocation (USD) | Progress (%)
Mon, Apr 8 | Planning | Finalize project scope and objectives | Alex Morgan | 8 | 6 | In Progress | 500 | 75%
Tue, Apr 9 | Design | Create wireframes and UI mockups | Jamie Lee | 12 | 10 | In Progress | 800 | 83%
Wed, Apr 10 | Development | Set up development environment | Sam Patel | 6 | 6 | Completed | 300 | 100%
Thu, Apr 11 | Testing | Conduct unit and integration tests | Taylor Reed | 10 | 8 | In Progress | 600 | 80%
Fri, Apr 12 | Review | Team review meeting and feedback collection | All Team Members | 4 | 4 | Completed | 200 | 100%