## Worksheet
Project ID | Project Name | Start Date | End Date | Budget (USD) | Actual Spend (USD) | Remaining Budget (USD) | Status | Owner | Primary Objective | Key Milestones | Risk Assessment | Dependencies | Forecasted Revenue (USD) | ROI Projection (%)
PM-2024-001 | Development of Smart City IoT Platform | 2024-03-15 | 2025-09-30 | $1,850,000 | $1,475,320 | $374,680 | On Track | Sarah Chen | Enable real-time urban monitoring and data analytics. | Q1 Launch MVP, Q3 Full Deployment, Q4 Integration with City Systems | Medium (Network latency) | Cloud infrastructure team, Municipal IT department | $2,100,000 | 28.5%
PM-2024-002 | Expansion of E-Services Portal | 2024-05-10 | 2025-11-30 | $950,000 | $892,450 | $57,550 | On Track | James Rodriguez | Improve citizen access to municipal services. | Phase 1 - Mobile App (Q2), Phase 2 - AI Chatbot (Q4) | Low (User adoption delay) | Customer Support Team, UX Design | $1,050,000 | 12.3%
PM-2024-003 | Renewable Energy Grid Upgrade | 2024-06-18 | 2026-12-31 | $5,200,000 | $4,789,150 | $410,850 | On Schedule (with delay) | Linda Patel | Increase energy efficiency and reduce carbon emissions. | Site assessment (Q1), Installation (Q3-Q4), Commissioning (Q5) | High (Regulatory changes) | Environmental Agency, Engineering Division | $6,800,000 | 19.2%